## DAP Tasks
Task Code | Task Name | Description | Attributes | Evidence Sources | Deliverable | Status | Created Date
YLC-2025-GI-01 | Topographic survey + chainage setup | Initial site survey | Attr 1, 5 | Survey report | Report | Achieved | 2025-03-15
YLC-2025-GI-02 | Geological mapping | Field mapping of slope | Attr 1 | Mapping report | Report | Achieved | 2025-04-01
YLC-2025-GI-03 | Trial pit excavation | 8 trial pits to 6m | Attr 1, 3 | Photos + log | Report | Achieved | 2025-04-15
YLC-2025-GI-04 | Soil sampling + lab testing | UD samples + classification | Attr 1 | Lab certificates | Report | Achieved | 2025-05-01
YLC-2025-GI-05 | Groundwater monitoring setup | Install piezometers | Attr 1, 2 | Installation cert | Report | Achieved | 2025-05-20
YLC-2025-Design-01 | Slope stability analysis (SLOPE/W) | Pre-failure analysis | Attr 1 | Calc report | Report | Achieved | 2025-06-10
YLC-2025-Design-02 | PLAXIS 3D model | FEM analysis | Attr 1, 7 | PLAXIS files | Model | Achieved | 2025-07-01
YLC-2025-Design-03 | Soil nail design | Design 120 nails | Attr 1, 6 | Design calcs | Report | Achieved | 2025-07-20
YLC-2025-Design-04 | Drainage design | Channel + U-drain | Attr 1, 4 | Design dwgs | Report | Achieved | 2025-08-01
YLC-2025-Design-05 | Maintenance Manual | Prepare manual | Attr 4, 5 | Manual doc | Manual | Achieved | 2025-08-15
YLC-2025-Design-06 | BD submission package | Submit to BD | Attr 1, 5, 6 | Submission letter | Submission | Achieved | 2025-09-01
YLC-2025-Design-07 | GEO comments response | Address GEO queries | Attr 5, 6 | Response letter | Report | Achieved | 2025-09-20
YLC-2025-Design-08 | BD approval received | Approval letter | Attr 1, 5 | BD letter | Letter | Achieved | 2025-10-15
YLC-2025-Tender-01 | Tender documents | Prepare tender | Attr 2, 5 | Tender doc | Tender | Achieved | 2025-11-01
YLC-2025-Tender-02 | Tender assessment | Evaluate bids | Attr 2, 6 | Assessment report | Report | Achieved | 2025-11-20
YLC-2025-Tender-03 | Contract award | Award to lowest bidder | Attr 2, 6 | Award letter | Letter | Achieved | 2025-12-01
YLC-2025-Const-01 | Site mobilization | Set up site office | Attr 2, 3 | Photos | Log | Achieved | 2025-12-15
YLC-2025-Const-02 | H&S plan review | Review H&S plan | Attr 3, 6 | Plan doc | Plan | Achieved | 2026-01-10
YLC-2025-Const-03 | Method statement review | Review MS | Attr 2, 3 | MS doc | Report | Achieved | 2026-01-20
YLC-2025-Const-04 | Risk assessment | Prepare RA | Attr 3, 6 | RA doc | Report | Achieved | 2026-02-01
YLC-2025-Const-05 | Permit to work system | Set up PTW | Attr 3 | PTW log | Log | Achieved | 2026-02-15
YLC-2025-Const-06 | Site supervision setup | RSE presence | Attr 2, 3, 7 | Site log | Log | Achieved | 2026-03-01
YLC-2025-Const-07 | Inclinometer baseline | Read initial | Attr 1, 5 | Baseline report | Report | Achieved | 2026-03-15
YLC-2025-Const-08 | Piezometer baseline | Read initial | Attr 1, 5 | Baseline report | Report | Achieved | 2026-03-15
YLC-2025-Const-09 | First bi-weekly monitoring | Submit report | Attr 1, 5 | Report | Report | Achieved | 2026-04-01
YLC-2025-Const-10 | Pit excavation start | Pit 1-5 | Attr 1, 3 | Site log | Log | Achieved | 2026-04-15
YLC-2025-Const-11 | Steel fixing inspection | Inspect rebar | Attr 1, 3 | Inspection log | Log | Achieved | 2026-05-01
YLC-2025-Const-12 | Formwork inspection | Inspect formwork | Attr 1, 3 | Inspection log | Log | Achieved | 2026-05-10
YLC-2025-Const-13 | Concrete pour 1 | Pour pit 1-5 | Attr 1, 3 | Cube tests | Log | Achieved | 2026-05-20
YLC-2025-Const-14 | Soil nail drilling start | Drill nails 1-10 | Attr 1, 3 | Drilling log | Log | Achieved | 2026-06-01
YLC-2025-Const-15 | Pull-out test witness | Witness tests | Attr 1, 3, 5 | Test cert | Cert | Achieved | 2026-06-05
YLC-2025-Const-16 | Monitoring week 8 | Continue I&M | Attr 1, 5 | Report | Report | Achieved | 2026-06-08
YLC-Remedial-01 | Pit-by-pit no-fines concrete replacement 施工監督 | Supervise pit-by-pit no-fines concrete replacement for YLC 11NW-A/C16. Review contractor method statements, inspect rebar placement, verify concrete strength (cube test), check plumb & alignment, ensure proper curing. | Attr 1, Attr 2, Attr 3, Attr 7 | Site photos (date-stamped) of each pit; Concrete cube test reports; Contractor daily site diary; RSE inspection records; Non-conformance reports (if any) | Inspection log + photo evidence + test certificates | Pending Review | 2026-06-09
YLC-Remedial-02 | Soil nail installation + pull-out test 監督與提交 | Supervise soil nail drilling, grouting, head construction. Witness pull-out tests per BD/GEO specifications. Compile and submit test reports with location plans. | Attr 1, Attr 3, Attr 5, Attr 6 | Drilling records (depth, diameter, soil profile); Grout mix design + cube tests; Pull-out test certificates; As-built location plan with nail IDs; Submission cover letter to BD | Soil nail pull-out test report + as-built plan | Pending Review | 2026-06-09
YLC-Monitoring-01 | Bi-weekly monitoring report 審核與提交 BD | Review contractor's bi-weekly monitoring data (inclinometers, piezometers, settlement markers, rain gauges). Compare with trigger levels. Compile report and submit to BD/GEO. | Attr 1, Attr 3, Attr 5, Attr 7 | Instrumentation readings (CSV + plots); Trigger level comparison table; Trend analysis with interpretations; Photographs of instruments; Cover letter to BD/GEO | Bi-weekly monitoring report (PDF) + cover letter | Pending Review | 2026-06-09
YLC-CPD-Leadership | 準備內部 lunch-and-learn (Yuet Lai Court case study) | Prepare and deliver internal technical presentation on YLC case study. Cover: DHO background, GI findings, design options, PLAXIS 3D / SLOPE/W analysis, soil nail design, lessons learned. Target audience: junior engineers. | Attr 7 | Presentation slides (PPT/PDF); Attendance register with names + signatures; Email announcement with date/time; Q&A summary; CPD hour log entry | Slides + attendance + CPD log entry (1-2 hrs CPD) | Pending Review | 2026-06-09
YLC-Sustainability-01 | Drainage re-check + Maintenance Manual 更新 + 綠化建議 | Re-check existing drainage system (channels, U-channels, catchpits). Update Maintenance Manual with current condition. Provide greening/landscape recommendations for sustainability. | Attr 2, Attr 4, Attr 5 | Drainage condition survey (photos + map); Updated Maintenance Manual (tracked changes); Greening recommendations memo; Sustainability assessment (carbon footprint, materials) | Updated Maintenance Manual + greening memo | Pending Review | 2026-06-09